## timelog
Project | Date | User | Activity | Issue | Comment | Hours
AI CERTs News | 08/30/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | Completed bugs related to text to speech | 8
AI CERTs News | 08/29/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | RnD on ionic to flutter | 8
AI CERTs News | 08/28/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | RnD on moodle map and ionic to flutter conversion Implement text to speech | 8
AI CERTs News | 08/27/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | RnD on moodle map, Implement text to speech | 8
AI CERTs News | 08/26/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | Tested fluttes tts and fixed bugs | 8
AI CERTs News | 08/23/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | Bug fixes in comment section | 8
AI CERTs News | 08/22/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | Fixed bugs related to image url Completed comment like | 8
AI CERTs News | 08/21/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | Completed authentication implemenation in certs 365(UI) Completed upload image bug | 8
AI CERTs News | 08/20/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | Fix LikeUnlikePosts concurrency on HomePage and Bookmark page | 8
AI CERTs News | 08/19/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | Fixed bugs related to navigation to enter otp screen and post content Started implementing text to speech | 8
AI CERTs News | 08/16/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | fixed bugs - Upload profile is not working correctly - keyboard on homepage has some extra space - Tap size on comments, like and bookmark is little small - if there is no comment the comment screen keeps loading. | 8
AI CERTs News | 08/15/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | Fixed on search tap feature | 8
AI CERTs News | 08/14/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | Added skeleton widgets and images avatar | 8
AI CERTs News | 08/13/2024 | Nikunj Chamaria | Development | Development #2908: News App and Web | Added skelton widgets and fixed profile page | 8
AI CERTs News | 2024-12-08 | Nikunj Chamaria | Development | Development #2908: News App and Web | Fixed crytp bubble bugs and added skeleton widget to mobile app | 8
AI CERTs News | 2024-09-08 | Nikunj Chamaria | Development | Development #2908: News App and Web | Fixed image bug and integrated get profile api | 8
AI CERTs News | 2024-08-08 | Nikunj Chamaria | Development | Development #2908: News App and Web | Compled crypto bubble changes | 8
AI CERTs News | 2024-07-08 | Nikunj Chamaria | Development | Development #2908: News App and Web | Completed comments api and started on upload image api | 8
AI CERTs News | 2024-06-08 | Nikunj Chamaria | Development | Development #2908: News App and Web | Worked on Crypto Table and readjusted the code | 9
AI CERTs News | 2024-05-08 | Nikunj Chamaria | Development | Development #2908: News App and Web | Added shimmers to post lisi added post comment functionality | 9
AI CERTs News | 2024-02-08 | Nikunj Chamaria | Development | Development #2908: News App and Web | Completed pagination for category page and added skeleton also fixed bugs for like post | 8
AI CERTs News | 2024-01-08 | Nikunj Chamaria | Development | Development #2908: News App and Web | Completed pagination for list of post and added images to post | 8